## Team Overview
SIMULATION 4-5 - TEAM WORK ALLOCATION
One Joined Project ¦ Production Quality Inspection System ¦ AdventureWorks2022
Course | SQL Server Developer |  |  | Database | AdventureWorks2022
Schema | ProductionOps |  |  | Timeline | 14 Days (one joined simulation)
Repo Folder | Simulation4-5/ |  |  | Team Size | 9 Members
Story Points | 22 per member (198 total) |  |  | Total Hours | 88
Detail Doc | work_allocated.md |  |  | Last Task | Sahil (deploy + submit)
JOINED TEAM ASSIGNMENTS (each task owned by ONE person)
# | Member | Role | Tasks Owned | Scripts / Deliverables | Story Pts | Total Hrs
1 | Hassana | Schema & Foundation Lead | L4-T1, L4-T2, L5-T10 | initialize_productionops_schema.sql inspection_request_registration.sql failed_inspection_queue.sql | 22 | 20
2 | Sahashri | Report & Batch Developer | L4-T10, L5-T6 | inspection_product_detail_report.sql inspection_batch_processing.sql | 22 | 12
3 | Brain | UDF & Control Flow Developer | L4-T3, L5-T3, L5-T4 | fn_InspectionScoreClass.sql inspection_result_classification.sql monthly_inspection_schedule.sql | 22 | 6
4 | Parth | Stored Proc & Error Handling | L4-T5, L5-T5 | usp_GetInspectionRequests.sql error_log.sql inspection_error_logging.sql | 22 | 11
5 | Josovo | Views & Analytics Developer | L4-T6, L4-T7, L5 support | vProductInspectionSummary.sql vw_PendingInspections.sql product_quality_statistics.sql | 22 | 6
6 | Lien | TVF & Table Developer | L4-T4, L5-T12 | fn_GetProductInspectionData.sql product_release_review.sql | 22 | 6
7 | Kelvin | Window Reports & Notification | L4-T8, L5-T7, L5-T13 | product_ranking_report.sql inspection_category_management.sql notification_log.sql inspection_notification_cursor.sql | 22 | 6
8 | Dhruv | Subquery & Cursor Developer | L4-T9, L5-T11 | products_below_safety_stock_report.sql failed_product_review_cursor.sql | 22 | 11
9 | Sahil | Final Deployment (LAST) | L4-T12-14, L5-T14 | deploy_lab4.sql validate_lab4_results.sql deploy_all.sql validate_lab5_results.sql README + Screenshots + QA | 22 | 11
TEAM TOTAL |  |  |  |  | 198 | 88

## All Scripts
SIMULATION 4-5 - ALL SCRIPTS
One repo: Simulation4-5/scripts/ ¦ Ordered by project day and phase
Day | Phase | Task | Script File | Folder | Owner | Type | Hours | Status
D1 | Phase 1 - Foundation | L4-T1 | initialize_productionops_schema.sql | Simulation4-5/scripts/setup/ | Hassana | Schema | 3 | Not Started
D1 | Phase 1 - Foundation | L4-T2 | inspection_request_registration.sql | Simulation4-5/scripts/tables/ | Hassana | Table | 3 | Not Started
D2 | Phase 1 - Reporting | L4-T3 | fn_InspectionScoreClass.sql | Simulation4-5/scripts/functions/ | Brain | Scalar UDF | 2 | Not Started
D2 | Phase 1 - Reporting | L4-T4 | fn_GetProductInspectionData.sql | Simulation4-5/scripts/functions/ | Lien | Table-Valued Function | 2 | Not Started
D2 | Phase 1 - Reporting | L4-T5 | usp_GetInspectionRequests.sql | Simulation4-5/scripts/procedures/ | Parth | Stored Procedure | 4 | Not Started
D2 | Phase 1 - Reporting | L4-T6 | vProductInspectionSummary.sql | Simulation4-5/scripts/views/ | Josovo | View | 1 | Not Started
D2 | Phase 1 - Reporting | L4-T6 | vw_PendingInspections.sql | Simulation4-5/scripts/views/ | Josovo | View | 1 | Not Started
D2 | Phase 1 - Reporting | L4-T7 | product_quality_statistics.sql | Simulation4-5/scripts/reporting/ | Josovo | CTE Report | 2 | Not Started
D3 | Phase 1 - Reporting | L4-T8 | product_ranking_report.sql | Simulation4-5/scripts/reporting/ | Kelvin | Window Functions | 2 | Not Started
D3 | Phase 1 - Reporting | L4-T9 | products_below_safety_stock_report.sql | Simulation4-5/scripts/reporting/ | Dhruv | Subquery Report | 4 | Not Started
D3 | Phase 1 - Reporting | L4-T10 | inspection_product_detail_report.sql | Simulation4-5/scripts/reporting/ | Sahashri | JOIN Report | 5 | Not Started
D4 | Phase 1 - Deploy | L4-T12 | deploy_lab4.sql | Simulation4-5/scripts/deployment/ | Sahil (LAST) | Mid-Project Deploy | 2 | Not Started
D4 | Phase 1 - Deploy | L4-T13 | validate_lab4_results.sql | Simulation4-5/scripts/validation/ | Sahil (LAST) | Validation | 1 | Not Started
D4 | Phase 1 - Deploy | L4-T14 | README Phase 1 section | Simulation4-5/ | Sahil (LAST) | Documentation | 1 | Not Started
D6 | Phase 2 - Control Flow | L5-T10 | failed_inspection_queue.sql | Simulation4-5/scripts/tables/ | Hassana | Table | 14 | Not Started
D6 | Phase 2 - Control Flow | L5-T6 | inspection_batch_processing.sql | Simulation4-5/scripts/temporary_objects/ | Sahashri | Temp Table | 7 | Not Started
D6 | Phase 2 - Control Flow | L5-T12 | product_release_review.sql | Simulation4-5/scripts/tables/ | Lien | Table | 4 | Not Started
D7 | Phase 2 - Control Flow | L5-T3 | inspection_result_classification.sql | Simulation4-5/scripts/controlflow/ | Brain | IF/ELSE | 2 | Not Started
D7 | Phase 2 - Control Flow | L5-T4 | monthly_inspection_schedule.sql | Simulation4-5/scripts/controlflow/ | Brain | WHILE | 2 | Not Started
D7 | Phase 2 - Control Flow | L5-T5 | error_log.sql | Simulation4-5/scripts/tables/ | Parth | Table | 3 | Not Started
D7 | Phase 2 - Control Flow | L5-T5 | inspection_error_logging.sql | Simulation4-5/scripts/errorhandling/ | Parth | TRY/CATCH | 4 | Not Started
D7 | Phase 2 - Control Flow | L5-T7 | inspection_category_management.sql | Simulation4-5/scripts/temporary_objects/ | Kelvin | Table Variable | 2 | Not Started
D9 | Phase 2 - Cursors | L5-T11 | failed_product_review_cursor.sql | Simulation4-5/scripts/cursors/ | Dhruv | Cursor | 7 | Not Started
D9 | Phase 2 - Cursors | L5-T13 | notification_log.sql | Simulation4-5/scripts/tables/ | Kelvin | Table | 1 | Not Started
D9 | Phase 2 - Cursors | L5-T13 | inspection_notification_cursor.sql | Simulation4-5/scripts/cursors/ | Kelvin | Cursor | 3 | Not Started
D11 | Phase 3 - Deploy | L5-T14 | deploy_all.sql | Simulation4-5/scripts/deployment/ | Sahil (LAST) | Full Deploy | 3 | Not Started
D11 | Phase 3 - Deploy | L5-T14 | validate_lab5_results.sql | Simulation4-5/scripts/validation/ | Sahil (LAST) | Validation | 2 | Not Started
D12 | Phase 3 - Submit | L5-T14 | README + Data Mapping + QA | Simulation4-5/ | Sahil (LAST) | Final Submission | 2 | Not Started
D11 | Phase 2 - Support | L5 support | Reporting validation | — | Josovo | Validation | 2 | Not Started
PROJECT TOTAL HOURS | [6 empty] | 91

## Dependencies
PROJECT DEPENDENCY MAP
Simulation 4-5 is one connected workflow — Phase 2 starts after mid deploy (Day 4)
Task | Owner | Depends On
L4-T1 Schema | Hassana | None
L4-T2 InspectionRequests | Hassana | L4-T1
L4-T3 Scalar UDF | Brain | L4-T1
L4-T4 TVF | Lien | L4-T1
L4-T5 Stored Procedure | Parth | L4-T2
L4-T6 Views | Josovo | L4-T1
L4-T7 CTE Report | Josovo | L4-T1
L4-T8 Window Report | Kelvin | L4-T1
L4-T9 Subquery Report | Dhruv | L4-T1
L4-T10 JOIN Report | Sahashri | L4-T1, L4-T2
L4-T12-14 Mid Deploy | Sahil (LAST) | ALL L4-T1 to T10
L5-T10 Failed Queue | Hassana | L4-T1
L5-T6 Temp Batch | Sahashri | L4-T1
L5-T3/T4 Control Flow | Brain | L4-T3 UDF
L5-T5 Error Logging | Parth | L4-T1
L5-T12 Release Review | Lien | L4-T1
L5-T7/T13 Notification | Kelvin | L5-T11
L5-T11 Review Cursor | Dhruv | L5-T10 + L5-T12
L5-T14 Final Submission | Sahil (LAST) | ALL scripts

## 14-Day Timeline
14-DAY PROJECT TIMELINE
Phase 1 (D1-5) ¦ Phase 2 (D6-11) ¦ Phase 3 (D12-14) ¦ Start: Jun 10, 2026
Day | Date | Phase | Member | Work Item | Exit Criteria | Hours | Status
D1 | 2026-06-10 | Phase 1 - Foundation | Hassana | L4-T1 Schema + L4-T2 InspectionRequests | Schema + 10+ rows | 6 | Not Started
D2 | 2026-06-11 | Phase 1 - Reporting | Brain | L4-T3 Scalar UDF | UDF tested | 2 | Not Started
D2 | 2026-06-11 | Phase 1 - Reporting | Parth | L4-T5 Stored Procedure | SP returns data | 4 | Not Started
D2 | 2026-06-11 | Phase 1 - Reporting | Josovo | L4-T6 Views + L4-T7 CTE | 2 views + CTE done | 4 | Not Started
D2 | 2026-06-11 | Phase 1 - Reporting | Lien | L4-T4 TVF | TVF tested | 2 | Not Started
D3 | 2026-06-12 | Phase 1 - Reporting | Kelvin | L4-T8 Window report | Ranking report done | 2 | Not Started
D3 | 2026-06-12 | Phase 1 - Reporting | Dhruv | L4-T9 Subquery report | Subquery report done | 4 | Not Started
D3 | 2026-06-12 | Phase 1 - Reporting | Sahashri | L4-T10 JOIN report | JOIN report done | 5 | Not Started
D4 | 2026-06-13 | Phase 1 - Deploy | Sahil (LAST) | L4-T12-14 Mid deploy + README | Mid deploy green | 4 | Not Started
D5 | 2026-06-14 | Phase 1 - Test | All | Test all Phase 1 scripts | Zero errors | 0 | Not Started
D6 | 2026-06-15 | Phase 2 - Control Flow | Hassana | L5-T10 Failed Queue | Queue populated | 14 | Not Started
D6 | 2026-06-15 | Phase 2 - Control Flow | Sahashri | L5-T6 Temp Batch | Batch script done | 7 | Not Started
D6 | 2026-06-15 | Phase 2 - Control Flow | Lien | L5-T12 Release Review table | Table DDL done | 4 | Not Started
D7 | 2026-06-16 | Phase 2 - Control Flow | Brain | L5-T3 + L5-T4 IF/ELSE + WHILE | Control flow done | 4 | Not Started
D7 | 2026-06-16 | Phase 2 - Control Flow | Parth | L5-T5 Error logging | TRY/CATCH working | 7 | Not Started
D7 | 2026-06-16 | Phase 2 - Control Flow | Kelvin | L5-T7 Table variables | Categories done | 2 | Not Started
D8 | 2026-06-17 | Phase 2 - Test | All except Sahil | Test own Phase 2 scripts | All pass | 0 | Not Started
D9 | 2026-06-18 | Phase 2 - Cursors | Dhruv | L5-T11 Review cursor | Queue processed | 7 | Not Started
D9 | 2026-06-18 | Phase 2 - Cursors | Kelvin | L5-T13 Notification cursor | Notifications done | 4 | Not Started
D10 | 2026-06-19 | Phase 2 - Handoff | All | Push all scripts to GitHub | Repo complete | 0 | Not Started
D11 | 2026-06-20 | Phase 3 - Deploy | Sahil (LAST) | L5-T14 deploy + validate | Full deploy green | 5 | Not Started
D11 | 2026-06-20 | Phase 3 - Deploy | Josovo | L5 support - reporting validation | Views + CTE verified | 2 | Not Started
D12 | 2026-06-21 | Phase 3 - Submit | Sahil (LAST) | README + screenshots + QA + submit | Link to professor | 2 | Not Started
D13-14 | 2026-06-22 | Buffer | All | Fix issues / final QA | Project complete | 0 | Not Started

## Member Quick Ref
MEMBER QUICK REFERENCE
Your complete Simulation 4-5 workload — see work_allocated.md for full detail
Member | Tasks Owned (Full Project) | Active Days | Depends On
Hassana | L4-T1, L4-T2, L5-T10 | D1 + D6 | None (start Day 1)
Sahashri | L4-T10, L5-T6 | D3 + D6 | L4-T1 + L4-T2 (Hassana)
Brain | L4-T3, L5-T3, L5-T4 | D2 + D7 | L4-T1 (Hassana)
Parth | L4-T5, L5-T5 | D2 + D7 | L4-T2 (Hassana)
Josovo | L4-T6, L4-T7, L5 support | D2 + D11 | L4-T1 (Hassana)
Lien | L4-T4, L5-T12 | D2 + D6 | L4-T1 (Hassana)
Kelvin | L4-T8, L5-T7, L5-T13 | D3 + D7 + D9 | L4-T1; L5-T11 (Dhruv)
Dhruv | L4-T9, L5-T11 | D3 + D9 | L5-T10 + L5-T12
Sahil (LAST) | L4-T12-14, L5-T14 | D4 + D11 + D12 | ALL scripts complete

## Member Detail
MEMBER DETAIL — WHO DOES WHAT
Day-by-day task breakdown per member (from work_allocated.md)
Member | Day | Task | Script | Folder | Hours | Screenshots
Hassana | D1 | L4-T1 | initialize_productionops_schema.sql | scripts/setup/ | 3 | Schema validation
Hassana | D1 | L4-T2 | inspection_request_registration.sql | scripts/tables/ | 3 | InspectionRequests data
Hassana | D6 | L5-T10 | failed_inspection_queue.sql | scripts/tables/ | 14 | FailedInspectionQueue data
Sahashri | D3 | L4-T10 | inspection_product_detail_report.sql | scripts/reporting/ | 5 | JOIN report output
Sahashri | D6 | L5-T6 | inspection_batch_processing.sql | scripts/temporary_objects/ | 7 | #InspectionBatch output
Brain | D2 | L4-T3 | fn_InspectionScoreClass.sql | scripts/functions/ | 2 | UDF test
Brain | D7 | L5-T3 | inspection_result_classification.sql | scripts/controlflow/ | 2 | IF/ELSE output
Brain | D7 | L5-T4 | monthly_inspection_schedule.sql | scripts/controlflow/ | 2 | WHILE schedule
Parth | D2 | L4-T5 | usp_GetInspectionRequests.sql | scripts/procedures/ | 4 | SP output
Parth | D7 | L5-T5 | error_log.sql + inspection_error_logging.sql | scripts/tables/ + errorhandling/ | 7 | ErrorLog contents
Josovo | D2 | L4-T6 | vProductInspectionSummary.sql + vw_PendingInspections.sql | scripts/views/ | 2 | View output
Josovo | D2 | L4-T7 | product_quality_statistics.sql | scripts/reporting/ | 2 | CTE statistics
Josovo | D11 | L5 support | Reporting validation | — | 2 | Re-run views after deploy
Lien | D2 | L4-T4 | fn_GetProductInspectionData.sql | scripts/functions/ | 2 | TVF output
Lien | D6 | L5-T12 | product_release_review.sql | scripts/tables/ | 4 | Table structure
Kelvin | D3 | L4-T8 | product_ranking_report.sql | scripts/reporting/ | 2 | Window ranking
Kelvin | D7 | L5-T7 | inspection_category_management.sql | scripts/temporary_objects/ | 2 | @InspectionCategories
Kelvin | D9 | L5-T13 | notification_log.sql + inspection_notification_cursor.sql | scripts/tables/ + cursors/ | 4 | NotificationLog
Dhruv | D3 | L4-T9 | products_below_safety_stock_report.sql | scripts/reporting/ | 4 | Subquery report
Dhruv | D9 | L5-T11 | failed_product_review_cursor.sql | scripts/cursors/ | 7 | Cursor + review data
Sahil (LAST) | D4 | L4-T12-14 | deploy_lab4.sql + validate_lab4_results.sql | scripts/deployment/ + validation/ | 4 | Mid deploy success
Sahil (LAST) | D11 | L5-T14 | deploy_all.sql + validate_lab5_results.sql | scripts/deployment/ + validation/ | 5 | Full deploy success
Sahil (LAST) | D12 | L5-T14 | README + screenshots + QA + submit | Simulation4-5/ | 2 | Final submission